## Risk Assessment
Risk Assessment
Perspiration-Responsive Motor Control for Urban E-Bikes — data collection ride protocol
Scoring: Risk score = Likelihood (1–5) × Impact (1–5). Bands: 1–4 Low, 5–9 Medium, 10–14 High, 15–25 Extreme. Likelihood and Impact each scale 1 = Very Low to 5 = Very High.
Risk ID | Risk Description | Category | Source | Impacted Stakeholder | Potential Impact | Likelihood (1–5) | Impact (1–5) | Score | Rating | Prevention Measures | Mitigation Response | Risk Owner | Key Assumption
1 | Rider involved in a road traffic collision | Safety | Traffic / public road | Test rider | Serious injury to rider from interaction with other road users. | 2 | 5 | 10 | High | Ride only on familiar commuting routes during daylight; obey all traffic law; maintain roadworthy brakes, lights, and tyres. | Follow the Highway Code; cease testing in poor visibility or heavy traffic. Rider holds appropriate experience for London roads. | Author | Rider is a competent, experienced urban cyclist.
2 | Motor continues to drive the wheel when the brakes are applied | Safety / Technical | Hardware / firmware | Test rider | Loss of speed control causing a crash and injury to the rider. | 1 | 5 | 5 | Medium | Inherited brake cut-off switches return the motor command to the 1.0 V idle baseline on brake engagement. | Bench-test and road-test the brake cut-off repeatedly before any data-collection ride; abort if behaviour is inconsistent. | Author | Brake cut-off hardware functions as specified.
3 | Rider distracted by the prototype interface while moving | Safety | User interface | Test rider | Attention diverted from the road, raising collision risk. | 2 | 4 | 8 | Medium | Interface configured before setting off and reviewed only after stopping; prediction and actuation run automatically with no input required while riding. | No interaction with the phone dashboard while in motion; pull over safely if any check is needed. | Author | Rider does not operate the interface while riding.
4 | Unexpected motor actuation surprises the rider | Safety / Technical | Control software | Test rider | A sudden assist change unsettles the rider and causes loss of control. | 2 | 4 | 8 | Medium | Assist increases are moderate and bounded by the legal envelope; sweat-reduction mode latches gradually after a 30 s sustained trigger rather than instantly. | Brake engagement immediately cancels any high-assist event; rider is briefed on expected actuation behaviour before the ride. | Author | Bounded, gradual assist changes remain controllable.
5 | Lithium-ion battery fire during a ride | Safety | Hardware (battery) | Test rider | Battery ignition causing burns or a crash. | 1 | 5 | 5 | Medium | Inspect the battery for visible damage, swelling, or heat before each ride; store and charge per manufacturer guidance. | Stop and dismount immediately if heat, smell, or smoke is detected; do not attempt to extinguish a Li-ion fire directly. | Author | Battery has been kept in good condition over its life.
6 | Electrical fault causes shock or fire | Safety | Hardware (wiring) | Test rider | Exposed or shorting connections injure the rider or damage hardware. | 1 | 4 | 4 | Low | All connections insulated and strain-relieved; enclosure secured to the down tube; DC-DC converter rated for the battery voltage. | Pre-ride visual check of all connections; isolate power at the 9-pin connector if a fault is suspected. | Author | Connections remain secure under ride vibration.
7 | Water ingress damages the non-waterproof electronics mid-ride | Safety / Technical | Hardware (enclosure) | Test rider | Sudden hardware failure mid-ride leading to loss of assist or a crash, plus loss of data. | 2 | 4 | 8 | Medium | Check the forecast before every ride; wet-weather riding is excluded from the test protocol. | If caught in rain, pause the ride, power down, and seek shelter; do not resume until the hardware is dry and checked. | Author | The exposed electronics are vulnerable to water.
8 | Mechanical failure of bike or mounting hardware mid-ride | Safety | Hardware (mechanical) | Test rider | Enclosure, sensor cabling, or bike component detaches and causes a crash. | 1 | 4 | 4 | Low | Enclosure and cabling secured with quick-release connectors and zip ties; routine pre-ride check of mounts and fasteners. | Stop riding if any rattle, looseness, or detachment is noticed; re-secure before continuing. | Author | Mounts hold under normal riding vibration.
9 | Rider unwell during a test, producing abnormal thermoregulatory response | Experimental | Rider physiology | Author (data quality) | Illness skews sweat response, contaminating training data. | 2 | 2 | 4 | Low | Self-screen for illness, fever, or dehydration before each ride; do not collect data when unwell. | Discard or flag any ride where the rider felt unwell so it can be excluded during cleaning. | Author | Rider honestly self-reports fitness to ride.
10 | Sweat sensor loses connection during a ride | Technical | Sensor / data pipeline | Author (data quality) | Gaps in the sweat-label stream reduce usable calibration data. | 3 | 2 | 6 | Medium | Seat the hDrop in the same position each ride; verify a live reading before setting off; log to local CSV as well as Supabase. | Flag affected rides; re-collect under similar conditions if the gap is significant. | Author | Brief dropouts do not invalidate an entire ride.
11 | Data collection system fails and ride data is lost | Technical | Cloud storage layer | Author (data quality) | Loss of logged rides reduces the training dataset. | 2 | 3 | 6 | Medium | Dual logging: every timestep written to local CSV as well as Supabase; cloud sync runs in a separate process so network delays cannot stall the control loop. | Recover from CSV backup after any cloud dropout; monitor connectivity rate across rides. | Author | Local backup captures data during network dropouts.
12 | Sweat sensor not reset, accumulating fluid loss from a prior ride | Experimental | Procedure | Author (data quality) | Inflated fluid-loss readings produce mislabelled rides. | 2 | 3 | 6 | Medium | Reset the hDrop at the start of every session as a fixed step in the pre-ride routine. | Cross-check measured fluid loss against the post-ride subjective rating; exclude inconsistent rides during cleaning. | Author | Reset-and-cross-check catches accumulation errors.
13 | Hygiene risk from skin-contact sweat sensor | Safety | Hardware (wearable) | Test rider | Skin irritation or contamination from a worn device. | 1 | 1 | 1 | Low | Clean the sensor contact surface with an alcohol wipe before and after each session. | Replace the wearable strap if visibly soiled or degraded. | Author | Alcohol wipes sufficiently clean the device.
14 | E-bike operates outside EAPC / EN 15194 legal limits | Regulatory | Hardware / firmware | Author / public | Bike reclassified as a motor vehicle, making road use illegal. | 1 | 4 | 4 | Low | Enforce 250 W rating, 25 km/h assist cut-off, and pedal-assist-only operation in the control logic; throttle-only operation removed at hardware level. | Test against key metrics (max assisted speed, cadence gating) before data collection; halt if limits are exceeded. | Author | Control logic reliably enforces the legal envelope.
15 | Improper handling of physiological data | Data / Privacy | Author (developer) | Test rider | Sweat and skin-temperature data exposed, lost, or mishandled. | 2 | 3 | 6 | Medium | Store no GPS, names, or direct identifiers; use anonymous ride IDs; treat physiological channels as sensitive per ICO guidance. | Restrict dataset access; define a retention policy; anonymise before any sharing. | Author | Sweat data is treated as health-adjacent data.